IHSAAN MEDICS

SRMA Student Portal

Content & Design Specification

For the website designer — complete content spec for all 4 phases of the student portal.

# How to use this document

This spec tells your designer exactly what goes on every page of the student portal, in what order, and what needs to be built vs uploaded. It covers:

- Global design principles: branding, colours, typography, sidebar and content area behaviour

- All 4 phases in full: every content item, its type, time estimate, description, and build status

- Gate logic: how and when each phase gate unlocks

- Additional portal pages: Resources, Supervisor Check-ins, Support

- Build priority order: what to build before launch vs just-in-time

STATUS CODES IN THE CONTENT TABLES Ready = file exists, upload immediately. To create = needs writing/recording before this phase goes live. Curate = link to or embed an existing free external resource (e.g. Cochrane Interactive Learning) — add only IHSAAN-specific framing around it.

# 1.  Global Design Principles

## Branding & Colours

| Role | Hex | Used for |
| --- | --- | --- |
| Primary teal | #1B6B6B | Phase banners, sidebar active state, buttons, badges, borders, heading colour |
| Light teal | #E8F4F4 | Callout backgrounds, sidebar active background, gate boxes |
| Mid teal | #A8D4D4 | Progress bars, dividers, hover states |
| White | #FFFFFF | Page background, card backgrounds, content area |
| Light grey | #F5F5F5 | Sidebar background, inactive item backgrounds |
| Dark | #1A1A1A | Body text, titles |
| Amber | #F5A623 | Gate items in sidebar, gate callout borders — signifies action required |

## Typography

Font family: Inter (preferred) or Poppins. Body text: 15–16px, line height 1.6. Headings: bold. Phase labels above titles: ALL-CAPS, teal, smaller. Keep it clean — lots of white space.

## Logo

IHSAAN MEDICS logo (mountain/ECG motif) top-left of the sidebar, same as current portal.

## Sidebar — Phase-Level Navigation

Each phase page has a left sidebar listing all content items for that phase in order. Mirrors the Meta Analysis Academy layout.

| Sidebar element | Spec |
| --- | --- |
| Phase progress bar | Shows X of Y items complete. Teal fill, light teal background. |
| Item: incomplete | White background, dark text, type badge (GUIDE, VIDEO, etc). Left border light grey. |
| Item: active | Teal background, white text. Left border thick teal. |
| Item: complete | Tick icon in teal. Text slightly muted. |
| Gate item | Amber/gold accent. Lock icon when locked; turns teal/green when unlocked. Gate items appear after the content items they depend on. |
| Collapse button | Arrow to collapse sidebar on narrower screens. |

## Main Content Area — Per-Item View

When a student clicks a sidebar item, the main area shows:

- Title of the item (large, bold)

- Type badge + estimated time (e.g. GUIDE · 20 min)

- Content: embedded PDF viewer, embedded video, inline form, or quiz

- Download button (for guides and templates)

- Mark as Complete button (teal, bottom right) — required before Gate unlocks

GATE LOGIC A Gate item only becomes clickable once every non-optional content item above it in that phase is marked complete. Show a locked padlock until then with the message: 'Complete all items above to unlock Gate X.'

PHASE 1 Foundations Weeks 1–2 · Deliverable: Approved feasible topic — Gate 1

## Phase 1 overview text (display at top of page)

PHASE 1 — FOUNDATIONS Welcome to Phase 1. Over the next two weeks you will get set up, understand what a systematic review is, confirm your research question is original and feasible, and submit your topic for supervisor approval at Gate 1. Budget about 3–5 hours across the fortnight.

## Phase 1 content items (sidebar order)

| TYPE | Content Item & Description | Time | Status |
| --- | --- | --- | --- |
| GUIDE | Welcome to the Programme Brief orientation: what the portal contains, how to navigate it, what to do first. A simple text/rich-text page — no download needed. | 10 min | Ready |
| GUIDE | What Is an SRMA? Introductory Guide (ST3) Plain-English: SR vs meta-analysis vs narrative synthesis; why SRMAs matter; what PRISMA and PROSPERO are; what each phase produces. Normalise narrative synthesis as a valid endpoint. | 20 min | To create |
| GUIDE | Your Project Workflow — Phase by Phase (ST4) Student-friendly map of all 4 phases: aim, tasks, deliverables, who signs off. Shows the full journey so students know where they are heading. | 15 min | To create |
| GUIDE | Software & Access Setup (ST10) Step-by-step: create Zotero and Rayyan accounts; access PubMed, PROSPERO, Cochrane CENTRAL (all free); OpenAthens login for Embase/Ovid. Done once in Week 1 — prerequisite for all later how-tos. | 30 min | To create |
| EXTERNAL | Curated Reading List (ST13) A rich-text page with links to: Cochrane Handbook, Cochrane Interactive Learning, PRISMA website, PROSPERO website, students' own university library SR guide. No download — just curated hyperlinks. | Browse | Ready |
| GUIDE | H1 · Scoping Search How to check your review doesn't already exist. Covers PROSPERO search for ongoing reviews + PubMed for published reviews + primary study volume check. Includes worked example and decision table. ALREADY WRITTEN — upload the existing H1 PDF. | 20 min | Ready |
| GUIDE | Worked Exemplar Review — Annotated (ST11) One well-conducted published systematic review, annotated page-by-page to show what 'good' looks like at each step. Highest-leverage teaching asset. Curate a suitable open-access review + add annotations as a PDF overlay or companion guide. | 45 min | To create |
| GUIDE | Critical Appraisal Mini-Guide (ST12) How to read a paper; using CASP checklists; spotting common flaws. Supports the Phase 1 deliverable of appraising an example paper. | 20 min | To create |
| QUIZ | Phase 1 Knowledge Check (ST14) 8–10 questions: difference between SR / MA / narrative synthesis; PROSPERO purpose; what PICO stands for; what a scoping search is for. Students must score ≥70% to unlock Gate 1. | 15 min | To create |

GATE 1 Topic Proposal & Feasibility Form (G4) Action: Student completes and submits the Topic Proposal & Feasibility Form. Supervisor receives a notification and signs off. Gate 1 turns green once supervisor approves.

NOTE TO DESIGNER The Knowledge Check (item 9) is the only hard prerequisite for Gate 1. Items 1–8 are self-paced. Show a progress count ('5 of 9 complete') at the top of the sidebar rather than hard-locking individual content items.

PHASE 2 Question & Protocol Weeks 3–5 · Deliverable: Registered PROSPERO protocol — Gates 2 & 3

## Phase 2 overview text

PHASE 2 — QUESTION & PROTOCOL You have a feasible topic. Now you will sharpen it into a precise PICO/PECO question, write your eligibility criteria, build a search strategy with a librarian, write your protocol to PRISMA-P standard, and register it on PROSPERO. Gates 2 and 3 are the protocol draft approval and PROSPERO registration confirmation.

## Phase 2 content items (sidebar order)

| TYPE | Content Item & Description | Time | Status |
| --- | --- | --- | --- |
| GUIDE | H2 · Framing Your Question with PICO/PECO Worked examples: translating a vague idea into a precise PICO (intervention) or PECO (exposure) question. Common mistakes: too broad, unmeasurable outcomes, non-specific populations. | 25 min | To create |
| GUIDE | H3 · Writing Eligibility Criteria Inclusion and exclusion criteria: how to write them so two people apply them identically. Good vs bad examples for each PICO element. | 20 min | To create |
| GUIDE | H4 · Building a Search Strategy MeSH vs free-text, Boolean logic (AND/OR/NOT), truncation, phrase searching, translating a PubMed strategy to Ovid/Embase/Cochrane. Worked example throughout. | 30 min | To create |
| GUIDE | H5 · Working with a Librarian Short guide: when and how to contact your university librarian. What to send them, what to ask, how to acknowledge them in your paper. | 10 min | To create |
| GUIDE | H6 · Writing Your Protocol (PRISMA-P) Walks through the PRISMA-P checklist item by item with plain-English explanation and example text for each section. Links to the downloadable PRISMA-P template. | 35 min | To create |
| TEMPLATE | Protocol Template (PRISMA-P) (ST16) Blank PRISMA-P protocol template (.docx) for students to complete. All required sections with placeholder text. Students download, fill in, and upload for Gate 2. | — | To create |
| GUIDE | H7 · Registering on PROSPERO Step-by-step walkthrough of the PROSPERO registration form. Notes what PROSPERO will and won't accept (no scoping reviews or pure literature reviews). Includes screen recording. | 20 min | To create |
| QUIZ | Phase 2 Knowledge Check (ST14) 8–10 questions: PICO elements; inclusion/exclusion criteria; Boolean operators; what PRISMA-P is; why PROSPERO registration matters. ≥70% to unlock Gate 2. | 15 min | To create |

GATE 2 Protocol Draft Approval Action: Student uploads completed PRISMA-P protocol draft. Supervisor reviews and approves (or returns with feedback). Gate 2 turns green once supervisor marks as approved.

GATE 3 PROSPERO Registration Confirmed Action: Student pastes their PROSPERO registration number into a text field. Gate 3 turns green automatically once a valid registration number is submitted.

PHASE 3 Screening & Synthesis Weeks 6–10 · Deliverable: Completed analysis — Gate 4

## Phase 3 overview text

PHASE 3 — SCREENING & SYNTHESIS This is the engine room. You will run your searches, import records into Zotero, screen titles/abstracts and full texts in Rayyan with your co-screener, extract data, assess risk of bias, and produce your synthesis (meta-analysis or narrative). It is the longest phase — allow 5+ hours per week.

## Phase 3 content items (sidebar order)

| TYPE | Content Item & Description | Time | Status |
| --- | --- | --- | --- |
| VIDEO | H8 · Running Searches & Exporting to Zotero Screen recordings (one per database): PubMed, Ovid/Embase, Cochrane CENTRAL. How to run your search and export results to Zotero. Produce as short screen recordings, not text guides. | 20 min | To create |
| VIDEO | H9 · Deduplicating Your Results Short demo: how to deduplicate your combined Zotero library before importing to Rayyan. | 10 min | To create |
| VIDEO | H10 · Screening in Rayyan Screen recording: Rayyan setup, importing records, blind dual screening, resolving conflicts. BUILD THIS FIRST — screening is where beginners stall most. A clear recording saves more support time than any other resource. | 25 min | To create |
| GUIDE | H11 · Full-Text Screening How to screen full texts, log exclusion reasons with PRISMA-compliant categories, and handle papers you can't access. | 15 min | To create |
| GUIDE | H12 · Making the PRISMA 2020 Flow Diagram Step-by-step using the free PRISMA 2020 flow diagram tool (prismastatement.org). How to fill in each box from your screening records. | 20 min | To create |
| GUIDE | H13 · Data Extraction Form How to design, pilot, and fill a data extraction form. Includes annotated example form. | 25 min | To create |
| TEMPLATE | Data Extraction Template (ST16) Blank extraction spreadsheet with standard columns: study ID, author, year, population, intervention, comparator, outcome, result, notes. | — | To create |
| GUIDE | H14 · Risk of Bias (RoB 2 & ROBINS-I) Modular: RoB 2 for RCTs; ROBINS-I for non-randomised studies; how to produce the robvis figure. Curate heavily from Cochrane Interactive Learning — add only IHSAAN-specific framing. | 30 min | Curate |
| GUIDE | H15 · Meta-analysis vs Narrative Synthesis Decision guide: when is pooling appropriate? What makes studies too heterogeneous? When is narrative synthesis the right call? Normalise narrative synthesis as a valid, publishable endpoint. | 15 min | To create |
| GUIDE | H16 · Running a Basic Meta-analysis Guide + screen recording: using RevMan or R (meta package) for a basic pooled analysis; reading a forest plot; interpreting I². Curate from Cochrane Interactive Learning. | 40 min | Curate |
| GUIDE | H17 · Structured Narrative Synthesis (SWiM) How to conduct and report a structured narrative synthesis using the SWiM framework. For teams whose data can't be pooled. | 25 min | To create |
| GUIDE | H18 · GRADE & Summary of Findings Table How to apply GRADE certainty ratings and build a Summary of Findings table in GRADEpro. Curate from GRADEpro tutorials. | 30 min | Curate |
| QUIZ | Phase 3 Knowledge Check (ST14) 8–10 questions on: dual screening rationale; PRISMA flow diagram boxes; RoB 2 domains; when to use meta-analysis vs narrative; what GRADE assesses. ≥70% to unlock Gate 4. | 15 min | To create |

GATE 4 Analysis Approved Action: Student uploads: completed PRISMA flow diagram, extraction sheet, risk-of-bias table, synthesis output (forest plot or narrative summary). Supervisor reviews and approves. Gate 4 unlocks Phase 4.

PHASE 4 Writing & Submission Weeks 11–16 · Deliverable: Submission-ready manuscript — Gates 5 & 6

## Phase 4 overview text

PHASE 4 — WRITING & SUBMISSION You have your analysis. Now you write the manuscript, get supervisor sign-off, select a journal (checking it is not predatory), and submit. The guaranteed programme deliverable is a complete, supervisor-approved manuscript draft. Submission and acceptance are aspirational outcomes that may continue beyond Week 16.

## Phase 4 content items (sidebar order)

| TYPE | Content Item & Description | Time | Status |
| --- | --- | --- | --- |
| TEMPLATE | Manuscript Template (ST7) Pre-structured Word document with all sections: Title, Structured Abstract, Introduction, Methods, Results, Discussion, Limitations, Conclusion, Declarations, Author Contributions, References, Tables & Figures, PRISMA 2020 Checklist, Supplementary Search Strategy. | — | To create |
| GUIDE | H19 · Writing Each Manuscript Section Section-by-section writing guide aligned to PRISMA 2020. What to include, common errors, example sentences for each section. | 45 min | To create |
| GUIDE | H20 · Citation Management in Zotero How to insert in-text citations and auto-generate a bibliography from Zotero in Word. Short screen demo included. | 20 min | To create |
| GUIDE | H21 · Choosing a Journal & Spotting Predators How to select an appropriate journal: scope, impact, open access. How to verify legitimacy using Think-Check-Submit and DOAJ. Red flags for predatory journals. | 20 min | To create |
| EXTERNAL | PRISMA 2020 Checklist Direct link to the official PRISMA 2020 checklist (prismastatement.org). Embed the PDF or link externally. Students must complete and upload this as part of submission. | — | Ready |
| GUIDE | H22 · Submitting Your Manuscript How to prepare submission files, write a cover letter, submit via the journal portal, and update the PROSPERO record to mark the review as completed. | 20 min | To create |
| GUIDE | H23 · Responding to Peer Review How to write a structured point-by-point response letter. How to approach major vs minor revisions. Managing the revision timeline. | 25 min | To create |
| QUIZ | Phase 4 Knowledge Check (ST14) 8–10 questions: PRISMA 2020 section requirements; what a cover letter contains; Think-Check-Submit purpose; what a point-by-point response letter is. ≥70% to pass. | 15 min | To create |

GATE 5 Supervisor Manuscript Approval Action: Student uploads full manuscript draft. Supervisor gives structured feedback (using Manuscript Review Rubric S4). Once supervisor marks as approved, Gate 5 turns green.

GATE 6 Submission Readiness — Programme Complete Action: Student confirms: Pre-Submission QA Checklist complete, all authors have approved the final version, journal selected and verified. Student uploads the completed PRISMA 2020 checklist. Gate 6 = programme completion. Issue a completion certificate or badge here.

# 2.  Additional Portal Pages

## Resources page

A library page accessible from the main left sidebar at all times, not gated by phase. Suggested content:

- Team Roles Sheet (ST5) — who does what in a review team. PDF or rich-text page.

- Authorship Explanation for Students (ST6) — blunt, fair explainer on how authorship is earned (not guaranteed).

- Contribution Log template (ST8) — downloadable spreadsheet; students update weekly. This is the evidence base for authorship disputes.

- Research Integrity & Authorship Policy (G2) — link to or embed the canonical policy document.

- Curated Reading List (ST13) — same as the Phase 1 item, also always accessible here.

## Supervisor Check-ins page

A timeline view of scheduled check-in points, mapped to week numbers:

- Wk 1 — Onboarding call (30 min)

- Wk 2 — PICO/feasibility approval → Gate 1

- Wk 4 — Protocol & search strategy review → Gate 2

- Wk 6 — PROSPERO registration confirmed → Gate 3

- Wk 8 — Extraction and synthesis direction check

- Wk 10 — Analysis approval → Gate 4

- Wk 12 — Manuscript outline review

- Wk 14–16 — Final manuscript review → Gate 5

Each check-in shows a status indicator: Upcoming / Complete. Consider a simple contact form for students to request an extra check-in.

## Support page

Contact email for the IHSAAN team, an FAQ accordion (common questions per phase), and a link to the pause/exit path explanation from the Student Handbook.

# 3.  Build Priority

What to build first — matched to what is needed before launch vs just-in-time per phase.

| Priority | What | Why |
| --- | --- | --- |
| 1 — Launch | Portal shell + Phase 1 page | Students need this from Day 1. Phase 1 has the most ready-to-upload content (H1 is already written and done). |
| 2 — Launch | Dashboard, Resources, Supervisor Check-ins, Support pages | Required to open applications and give students a complete first-day experience. |
| 3 — Before Wk 3 | Phase 2 page | Goes live just before Phase 2 starts. Students don't need it until then. |
| 4 — Before Wk 6 | Phase 3 page | Build H10 (Rayyan screen recording) first within Phase 3. |
| 5 — Before Wk 11 | Phase 4 page | Can be built while Cohort 1 is in Phase 3. |

QUESTION FOR YOUR DESIGNER What platform is the portal built on? (Webflow, a custom CMS, Teachable, Notion, etc.) The gate/completion logic requires tracking per-student item completion. Confirm whether the platform supports this natively or whether a workaround is needed before agreeing on the build approach.